## Credential Validation
Premier — Credential Validation Report
Date | 2026-07-28
Project | Premier Receiver Automation
Activity | Validation of all required access credentials
Logged in | Email-Planner-Tracker.xlsx > sheet 'Premier 28-Jul-2026', row 26 (Closed)
Prepared by | Ashford (Conscious Creations)
Evidence labels: VERIFIED LIVE = independently confirmed in-session via a live call ¦ REPORTED = confirmed by the team, not independently re-tested here
1. Summary
All three credential sets required to begin live pipeline work against Premier were validated today: the Outlook receiving mailbox, Azure DevOps, and the Spitfire VM. This clears the last standing access prerequisites for Stage 1 ingest against the real mailbox.
# | Credential / access | Result | Evidence
1 | Outlook mailbox — receiver@premierpm.com (Microsoft Graph) | WORKING — read + write/move | VERIFIED LIVE
2 | Azure DevOps | Validated | REPORTED
3 | Spitfire VM | Validated | REPORTED
2. Detail — Outlook mailbox (VERIFIED LIVE, read-only Graph check)
App-only token acquired (app 'Conscious Creations', tenant [REDACTED]). Granted role: Mail.ReadWrite (read messages/bodies/attachments AND move/file mail). Token call + HTTP GETs only — nothing written to the mailbox.
Check | Result
List mail folders | allowed (8 folders)
Read Inbox metadata | allowed — Inbox, 6 items
List latest messages | allowed (5 returned)
List Inbox messages | allowed (3 returned)
Read a message body | allowed
List attachments (PODs) | NOT exercised — no message with an attachment present
Note: the 2026-07-14 exhaustive probe showed ZERO permissions; as of today Mail.ReadWrite is granted and working against the live mailbox.
2. Detail — Azure DevOps & Spitfire VM (REPORTED)
Azure DevOps: access validated by the team today; not independently re-tested in this session. Supports the SoW commitment that all source is checked into Premier's Azure DevOps.
Spitfire VM: VM access validated by the team today; not independently re-tested. Gateway to the Spitfire REST/SQL integration that Stages 4-7 depend on. VM access is distinct from the Spitfire Swagger + service account + published SQL still needed to build the connector.
3. Current mailbox contents (observed today)
Mailbox is reachable but holds NO delivery/receiving mail yet — 8 messages total, all internal Premier HR/admin notices (Monthly Huddle x4, a canceled reward, a Spexx update, two group-calendar invites), none with attachments. Implication: access is proven, but there is no real test material. Representative delivery e-mails — ideally at least one with a PDF/POD attachment — are needed to validate ingest/extract end-to-end.
4. Open items (not blockers to today's result)
# | Item | Owner | Note
1 | Confirm Exchange Application Access Policy scopes the app to only receiver@premierpm.com | Premier (Joe) | Mail.ReadWrite is tenant-wide until applied; check via Get-ApplicationAccessPolicy
2 | Prove POD attachment download end-to-end | Conscious Creations | Permitted by role but never executed — needs a test e-mail with an attachment
3 | Seed the mailbox with representative delivery e-mails | Premier / CC | Required to tune triage against real mail
4 | Spitfire Swagger + service account + published SQL | Premier (Joe) | VM access != API/SQL access; still needed for Stages 4-7
5. Next step
With mailbox, DevOps and Spitfire VM access confirmed, Stage 1 ingest can be pointed at the live mailbox for a first real run once (a) the Application Access Policy is confirmed and (b) sample delivery mail is available to process.
Recorded 2026-07-28. The Outlook mailbox result was verified live via a read-only Microsoft Graph check; Azure DevOps and Spitfire VM results are as reported by the team. No mailbox item was read into storage, moved, marked read or deleted.